## Timeline
TASK NAME | SUB TASK NAME | STATUS | START DATE | END DATE | DURATION in days | COMMENTS / FEEDBACK
Senior Thesis Research Proposal | Assignment 1 | Completed | 2025-08-18 | 2025-09-04 | 17
Literature Review Section for your Thesis Project | Assignment 2 | Completed | 2025-09-04 | 2025-09-18 | 14
Status Report #1 | Set up Kaggle coding environment. Load required libraries and data files. Filter data (NBA only, seasons ≥ 2000). Deliverable: Data fully loaded and ready for cleaning. | Completed | 2025-09-18 | 2025-09-25 | 7 | Insights Documentation: Summarize your "Insights" to clearly define whether they are findings, visualizations, or hypotheses for better progress tracking. Data Cleaning: Document your method for handling missing values (e.g., dropping rows, imputation) to ensure transparency. Transition to GitHub: Create a complete GitHub repository with a README, code, cleaned data, and documentation to ensure your work is reproducible and easy to follow. Next Week's Plan: Define and break down specific upcoming tasks like feature engineering or visualization to stay focused and measure progress.
Status Report #2 | Clean data (handle missing values). Subset data (by year, team, bench players, role players, and veterans). Create features (minutes per game, assist-to-turnover ratio, player experience). Deliverable: Clean, organized dataset ready for analysis. Transition to GitHub | Started | 2025-09-25 | 2025-10-02 | 7
Final assignment |  | Not Started | 2025-10-02 | 2025-12-18 | 77
Status Report #3 | Analyze Insights 1–3. Generate stats, graphs, and charts. Deliverable: Completed analysis visuals for Insights 1–3. | Not Started | 2025-10-02 | 2025-10-09 | 7
Status Report #4 | Analyze Insights 4–6. Generate stats, graphs, and charts. Deliverable: Completed analysis visuals for Insights 4–6. | Not Started | 2025-10-09 | 2025-10-16 | 7
Status Report #5 | Run statistical tests and correlations for Insights 1–4. Begin drafting thesis (focus on these results). Deliverable: Draft sections for Insights 1–4. | Not Started | 2025-10-16 | 2025-10-23 | 7
Thesis Paper First Draft | Assignment 3 | Not Started | 2025-09-18 | 2025-10-23 | 35
Status Report #6 | Run statistical tests and correlations for Insights 5–6. Continue thesis draft. Deliverable: Draft sections for Insights 5–6. | Not Started | 2025-10-23 | 2025-10-30 | 7
Status Report #7 | Review code for errors and accuracy. Verify that results are properly represented. Continue working on thesis draft. Deliverable: Near-complete thesis draft, checked for accuracy. | Not Started | 2025-10-30 | 2025-11-06 | 7
Status Report #8 | Validate thesis against project requirements. Finalize and submit draft thesis. Deliverable: Submitted draft thesis. | Not Started | 2025-11-06 | 2025-11-13 | 7
Status Report #9 | Review feedback from draft thesis. Apply revisions. Prepare narrated presentation. Deliverable: Final thesis completed and presentation drafted. | Not Started | 2025-11-13 | 2025-11-20 | 7
Status Report #10 | Submit final thesis. Finalize and submit narrated presentation. Deliverable: Completed project with thesis and presentation submitted. | Not Started | 2025-11-20 | 2025-12-04 | 14
Thesis Paper Final Draft | Assignment 4 | Not Started | 2025-10-23 | 2025-12-04 | 42
Final Thesis Narrated Presentation |  | Not Started | 2025-12-04 | 2025-12-11 | 7
0

## Insights
Defensive Metrics and Team Success
Leverage defensive statistics alongside team performance data.
Provide insights into how defensive contributions critically influence team success.
Role Player Efficiency and Team Success
Compare bench player production against starters.
Show the value of efficient bench production in sustaining team success.
Player Efficiency and Experience
Assess whether veterans (7+ years in the league) provide efficiency benefits.
Explore correlations between player experience, minutes played, and production.
Role Player Versatility and Offensive Efficiency
Focus on role players (Usage 10–15%).
Measure their impact through shooting percentage, assist-to-turnover ratio, and free-throw percentage.
Highlight the importance of versatile and efficient role players.
Bench Strength and End-of-Season Standings
Aggregate team bench efficiency metrics.
Correlate these with season standings and postseason results.
Show how bench production acts as a “quiet star” for team success.
Role Player Depth and End-of-Season Standings
Average each team’s role player efficiency.
Tie results to end-of-season and postseason performance.
Demonstrate how depth and role players elevate overall team outcomes.

## Feedback
Insights Documentation
Consider briefly summarizing what “Insights 1 & 2” refer to—whether they’re statistical findings, visualizations, or hypotheses. This will help track your analytical progress.
Data Cleaning
Document your approach to handling missing values—did you drop rows, impute values, or use domain-specific logic? This will be important for transparency.
Transition to GitHub
When you move to GitHub, include a README.md with project goals, dataset sources, and a changelog. This will make your work easier to follow and share.
For full points, ensure your GitHub repository includes code, cleaned datasets, and documentation. This will help with version control and reproducibility.
Next Week’s Plan
Define specific tasks such as feature engineering, exploratory visualizations, or model setup. This will help you stay focused and make your progress easier to assess.
Detailed breakdown